## Sheet1
Planned date for queen to emerge |  |  | 2024-05-31
|  | Day | Activity | Comment
| 2024-04-19 | -42 | Complete disease inspection and assess varroa populations. | The colonies must be healthy and disease free.
| 2024-04-19 | -42 | Drone foundation into drone producing colonies. | Drones take 2 weeks to sexually mature after emerging. Feed colonies well.
| 2024-04-26 | -35 | Set up cell raiser to be a strong, double brood colony. | Box of foundation on an already strong colony
Feed colony well.
Make sure colony has adequate pollen supplies.
| 2024-05-09 | -22 | Introduce frame of foundation to cell donor | Bees to draw out and queen to lay eggs so larva is just 24 hours old when time to cut miller frame
| 2024-05-10 | -21 | Introduce cloake board to cell raiser colony. | Allow the colony plenty of time to settle down to the new configuration.
Change entrance so the bees use the cloake board entrance
| 2024-05-12 | -19 | Introduce 2nd frame of foundation to cell donor | Bees to draw out and queen to lay eggs rso larva is just 24 hours old when time to cut miller frame. Insurance policy to try and make sure we have correct larva for miller frame.
| 2024-05-17 | -14 | Prepare the cell raiser colony. | Get as many nurse bees as possible into the top box.
|  |  | Lift frame(s) of open brood to the top brood box. | Bleed flying bees from the bottom box into the top box.
|  |  | 2 or 3 hours later insert the cloake board slide and open the floor rear entrance. | Make top brood box effectively queenless and very congested with bees.
| 2024-05-18 | -13 | Select suitable frame from the cell donor. Cut the miller frame. | Eggs should be starting to hatch.
Introduce the cut frame to the cell raiser
| 2024-05-19 | -12 | Check queen cells started on the miller frame. | Cell raiser has been returned to a single queen right colony.
|  |  | Remove slide and close rear entrance in the floor. | The bees will continue to nurture the queen cells.
| 2024-05-22 | -9 | Inspect cell raiser to make sure no emergency/rogue queen cells. | Essential that the only queen cells are on the miller frame.
| 2024-05-25 | -6 | Create mating colonies.
| 2024-05-30 | -1 | Move mature queen cells to mating colonies | Protect their sides with aluminium foil (or similar)
| 2024-05-31 | 0 | Queen cells emerge
| 2024-06-14 | 14 | Check for eggs being laid in mating colonies